## Table 1 - AHSP Years 1-5
MORE HOMES DIVISION
STRATEGIC HOUSING INVESTMENT PLAN 2026/27 - 2030/31
Table 1 - AFFORDABLE HOUSING SUPPLY PROGRAMME - Years 1-5 2026/27 - 2030/31
LOCAL AUTHORITY: Midlothian
PROJECT | SUB-AREA | PRIORITY | GEOGRAPHIC COORDINATES (X:EASTING Y:NORTHING) | GEOGRAPHIC CODE (Numeric Value - from Drop Down Table Below) | DEVELOPER | UNITS - TENURE | [6 empty] | UNITS - BUILT FORM |  |  |  | UNITS - TYPE |  |  |  | GREENER STANDARDS | APPROVAL DATE | UNITS SITE STARTS | [5 empty] | UNITS SITE COMPLETIONS | [5 empty] | SG AHSP FUNDING REQUIREMENT (£0.000M)
|  | Low / Medium / High |  |  |  | Social Rent | Mid Market Rent | LCHO - Shared Equity | LCHO - Shared Ownership | LCHO - Improvement for Sale | PSR | Total Units | Rehab | Off the Shelf | NB | Total Units | GN | Specialist Provision | Type of Specialist Particular Need (If Known) | Total Units by Type | Enter Y or N | Financial Year (Estimated or Actual) | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31 | TOTAL SITE STARTS OVER PERIOD OF SHIP | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31 | TOTAL COMPLETIONS OVER PERIOD OF SHIP | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31 | TOTAL AHSP FUNDING REQUIRED OVER SHIP PERIOD
Plot P,Shawfair: P43738 | B | High | X:331479 Y:668973 | 5 | Midlothian Council | 38 | [5 empty] | 38 |  |  | 38 | 38 | 38 |  |  | 38 | Y | 2025/26 | 38 |  |  |  |  | 38 |  | 38 |  |  |  | 38 | 1.75 | 1.75 |  |  |  | 3.5 | checked on HARP, up to date
Edmonstone Road, Danderhall: P43720 | B | High | X: 330444 Y: 669939 | 3 | Midlothian Council | 28 | [5 empty] | 28 |  |  | 28 | 28 | 28 |  |  | 28 | Y | 2025/26 | [5 empty] | 0 | 28 |  |  |  |  | 28 | 1.797 |  |  |  |  | 1.797 | checked on HARP, up to date
Rullion Road, Penicuik: P46386 | A | High | X: 332062 Y: 660343 | 2 | Midlothian Council | 48 | [5 empty] | 48 |  |  | 48 | 48 | 47 | 1 | Wheelchair accessible housing | 48 | Y | 2026/27 | 48 |  |  |  |  | 48 |  | 48 |  |  |  | 48 | 2.267 | 2.267 |  |  |  | 4.534 | MHD acquisition in 25/26
Lingerwood: P41724 | B | Medium | X: 334116 Y: 663691 | 2 | Midlothian Council | 113 | [5 empty] | 113 |  |  | 113 | 113 | 111 | 2 | TBC | 113 | Y | 2026/27 | 44 |  | 35 |  | 34 | 113 |  | 44 |  |  | 35 | 79 | 2.078 | 2.078 | 1.653 | 1.653 |  | 7.462 | updated as per meeting 18/6/25
Auchendinny, Phase 1: P43835 | A | High | X: 325522 Y: 662254 | 2 | Midlothian Council | 25 | [5 empty] | 25 |  |  | 25 | 25 | 25 |  |  | 25 | Y | 2026/27 | 25 |  |  |  |  | 25 |  | 25 |  |  |  | 25 | 2.361 |  |  |  |  | 2.361 | Grant req correct and updated as per B.S
Auchendinny, Phase 2: P48309 | A | High | X: 325522 Y: 662254 | 2 | Midlothian Council | 23 | [5 empty] | 23 |  |  | 23 | 23 | 23 |  |  | 23 | Y | 2027/28 | 23 |  |  |  |  | 23 |  | 23 |  |  |  | 23 |  | 2.172 |  |  |  | 2.172 | updated as per B.S
Auchendinny, Phase 3: P48310 | A | High | X: 325522 Y: 662254 | 2 | Midlothian Council | 27 | [5 empty] | 27 |  |  | 27 | 27 | 27 |  |  | 27 | Y | 2028/29 | 27 |  |  |  |  | 27 |  |  | 27 |  |  | 27 |  |  | 2.55 |  |  | 2.55 | updated as per B.S
Newbyres Crescent, Gorebridge: T34262 | B | approved for funding | X: 334476 Y: 661897 | 2 | Midlothian Council | 75 | [5 empty] | 75 |  |  | 75 | 75 | 62 | 13 | Extra Care, Bariatric and Wheelchair Bungalow | 75 | Y | 2017/18 | [5 empty] | 0 | 75 |  |  |  |  | 75 | [5 empty] | 0 | full claim complete, units scheduled for comp June 26
Polton Street, Bonnyrigg, Complex Care: P41758 | B | approved for funding | X: 330668 Y: 665025 | 2 | Midlothian Council | 46 | [5 empty] | 46 |  |  | 46 | 46 |  | 46 | Complex Care | 46 | Y | 2024/25 | [5 empty] | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 | full claim complete and units complete in 2025
Easthouses Road, former Newbattle High School, Mayfield, phase 1: P42523 | B | approved for funding | X: 334483 Y: 665085 | 2 | Midlothian Council | 90 | [5 empty] | 90 |  |  | 90 | 90 | 84 | 6 | WFS, Wheelchair House | 90 | Y | 2023/24 | [5 empty] | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 | full claim complete and units complete in 2025
Newton Church Road, Danderhall, former leisure centre: P43833 | B | approved for funding | X: 330832 Y: 669312 | 5 | Midlothian Council | 23 | [5 empty] | 23 |  |  | 23 | 23 |  | 23 | Amenity/WFS | 23 | Y | 2025/26 | [5 empty] | 0 | 23 |  |  |  |  | 23 | [5 empty] | 0 | full claim complete. Units scheduled for comp Sept 26
Church Halls and Main Street, former swimming pool, Newtongrange: P43742 | B | High | X: 333394 Y: 664301 | 2 | Midlothian Council | 23 | [5 empty] | 23 |  |  | 23 | 23 | 23 |  |  | 23 | Y | 2026/27 | 23 |  |  |  |  | 23 |  | 23 |  |  |  | 23 | 0.9405 | 0.9405 |  |  |  | 1.881 | full grant minus £291080 payment
Plot AA2/AA3, Newton Church Road, Millerhill: T36399 | B | approved for funding | X:330693, Y:670240 | 5 | Midlothian Council | 34 | [5 empty] | 34 |  |  | 34 | 34 | 34 |  |  | 34 | Y | 2025/26 | 0 |  |  |  |  | 0 | 0 |  |  |  |  | 0 | 3.643 |  |  |  |  | 3.643 | checked on HARP. All up to date
Cauldcoats: P41960 | B | Medium | X - 330663 Y - 670906 | 5 | Midlothian Council | 50 | [5 empty] | 50 |  |  | 50 | 50 | 50 |  |  | 50 | Y | 2027/28 |  | 50 |  |  |  | 50 |  |  | 50 |  |  | 50 |  | 2.4783 | 2.4783 |  |  | 4.9566 | 50 x rural
Open Market Purchases | A and B | High | Various | various | Midlothian Council | 30 | [5 empty] | 30 |  | 30 |  | 30 | 29 | 1 | Amenity Bungalow | 30 | Y | 2017/18 | [5 empty] | 0 | 0 |  |  |  |  | 0 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 1.65 | 6 @ £55k/OMP
Oakwood Edge, Mayfield: P40161 | B | High | X-334128 Y-665169 | 5 | Melville | 8 | [5 empty] | 8 |  |  | 8 | 8 | 8 |  |  | 8 | Y | 2026/27 | 8 |  |  |  |  | 8 |  | 8 |  |  |  | 8 | 0.911 |  |  |  |  | 0.911
Bilston 3a (TW): P41762 | A | High | X-326129 Y-665282 | 3 | Melville |  | 18 |  |  |  |  | 18 |  |  | 18 | 18 | 18 |  |  | 18 | Y | 2026/27 | 18 |  |  |  |  | 18 | 18 |  |  |  |  | 18 | 1.495 |  |  |  |  | 1.495
Bannock Wood, Bonnyrigg 1 (TW): P47222 | B | High | X329838 Y-663960 | 2 | Melville |  | 38 |  |  |  |  | 38 |  |  | 38 | 38 | 30 | 8 | Ambulant | 38 | Y | 2026/27 | 38 |  |  |  |  | 38 |  | 38 |  |  |  | 38 | 0.4 | 2.5 |  |  |  | 2.9
Bilston 3b (TW): P47225 P47226 | A | High | X-325959 Y-665087 | 3 | Melville | 20 | 16 |  |  |  |  | 36 |  |  | 36 | 36 | 32 | 4 | Ambulant | 36 | Y | 2027/28 |  | 36 |  |  |  | 36 |  | 9 | 27 |  |  | 36 |  | 3.4 |  |  |  | 3.4
Bannock Wood, Bonnyrigg 2 (TW): P47224 | B | High | X-330161 Y-663979 | 2 | Melville | 53 | [5 empty] | 53 |  |  | 53 | 53 | 45 | 8 | Ambulant | 53 | Y | 2027/28 |  | 53 |  |  |  | 53 |  | 18 | 35 |  |  | 53 |  | 2.9 | 3.015 |  |  | 5.915
Old School Crescent, Mayfield 1: P41923 | B | High | X-335148 Y-665882 | 2 | Melville | 30 | [5 empty] | 30 |  |  | 30 | 30 | 27 | 3 | Wheelchair | 30 | Y | 2028/29 |  |  | 30 |  |  | 30 |  |  |  | 30 |  | 30 |  |  | 3.1 | 0.6 |  | 3.7
Old School Crescent, Mayfield 2: P44239 | B | High | X-335148 Y-665882 | 2 | Melville | 31 | [5 empty] | 31 |  |  | 31 | 31 | 27 | 4 | Ambulant | 31 | Y | 2029/30 |  |  |  | 31 |  | 31 |  |  |  |  | 31 | 31 |  |  |  | 3.6 | 0.3 | 3.9
Cauldcoats Phase 1 Social Rent: P43188 | B | Medium | X - 330663 Y - 670906 | 5 | PFP | 39 | [5 empty] | 39 |  |  | 39 | 39 | 39 |  | TBC | 39 | Y | 2026/27 | 24 | 15 |  |  |  | 39 |  | 8 | 31 |  |  | 39 | 3.336 | 2.085 |  |  |  | 5.421
Cauldcoats Phase 1 MMR: P47831 | B | Medium | X - 330663 Y - 670906 | 5 | PFP |  | 39 |  |  |  |  | 39 |  |  | 39 | 39 | 39 |  |  | 39 | Y | 2026/27 | 7 | 16 | 16 |  |  | 39 |  |  | 17 | 14 | 8 | 39 | 0.686 | 1.568 | 1.568 |  |  | 3.822
Cauldcoats Phase 2 Social Rent: P43837 | B | Medium | X - 330663 Y - 670906 | 5 | PFP | 29 | [5 empty] | 29 |  |  | 29 | 29 | 29 |  | TBC | 29 | Y | 2028/29 |  |  |  | 29 |  | 29 |  |  |  | 22 | 7 | 29 |  |  |  | 4.031 |  | 4.031
Cauldcoats Phase 2 - MMR: P43838 | B | Medium | X - 330663 Y - 670906 | 5 | PFP |  | 19 |  |  |  |  | 19 |  |  | 19 | 19 | 19 |  |  | 19 | Y | 2028/29 |  |  |  | 19 |  | 19 |  |  |  | 10 | 9 | 19 |  |  |  | 1.862 |  | 1.862
Cauldcoats Phase 3 Social Rent: P41930 | B | Medium | X - 330663 Y - 670906 | 5 | PFP | 22 | [5 empty] | 22 |  |  | 22 | 22 | 22 |  | TBC | 22 | Y | 2029/30 |  |  |  |  | 22 | 22 | [5 empty] | 0 |  |  |  |  | 2.156 | 2.156
Cauldcoats Phase 3 - MMR: P41774 | B | Medium | X - 330663 Y - 670906 | 5 | PFP |  | 12 |  |  |  |  | 12 |  |  | 12 | 12 | 12 |  |  | 12 | Y | 2029/30 |  |  |  |  | 12 | 12 | [5 empty] | 0 |  |  |  |  | 1.176 | 1.176
Shawfair Woolmet W2 - Phase 1 - Social Rent: P48326 | B | High | X - 331679 Y - 669332 |  | PFP | 11 | [5 empty] | 11 |  |  | 11 | 11 | 11 |  |  | 11 | Y | 2026/27 | 11 |  |  |  |  | 11 | 11 |  |  |  |  | 11 | 1.335 |  |  |  |  | 1.335
Shawfair Woolmet W1 - Phase 2 - Social Rent: P44575 | B | High | X - 331485 Y - 669558 |  | PFP | 18 | [5 empty] | 18 |  |  | 18 | 18 | 18 |  |  | 18 | Y | 2027/28 |  | 18 |  |  |  | 18 |  |  | 18 |  |  | 18 |  | 1.311 | 0.874 |  |  | 2.185
Shawfair Woolmet W1 - Phase 2 - MMR: P47227 | B | High | X - 331485 Y - 669558 |  | PFP |  | 15 |  |  |  |  | 15 |  |  | 15 | 15 | 15 |  |  | 15 | Y | 2027/28 |  | 15 |  |  |  | 15 |  |  | 15 |  |  | 15 |  | 0.797 | 0.531 |  |  | 1.328
Shawfair R1/R2 - Social Rent: P43739 | B | High | X - 332524 Y - 669692 |  | PFP | 26 | [5 empty] | 26 |  |  | 26 | 26 | 26 |  |  | 26 | Y | 2025/26 | [5 empty] | 0 |  | 26 |  |  |  | 26 | [5 empty] | 0 | CB FUNDED
Shawfair R1/R2 - MMR: P42532 | B | High | X - 332524 Y - 669692 |  | PFP |  | 9 |  |  |  |  | 9 |  |  | 9 | 9 | 9 |  |  | 9 | Y | 2025/26 | [5 empty] | 0 |  | 9 |  |  |  | 9 | 0.777 |  |  |  |  | 0.777
Shawfair Bellway Plots E2 & F1 - SR - Phase 1: P44793 | B | Medium | X - 331600 Y - 669798 |  | PFP | 26 | [5 empty] | 26 |  |  | 26 | 26 | 26 |  |  | 26 | Y | 2026/27 | 26 |  |  |  |  | 26 |  |  | 26 |  |  | 26 | 2.643 | 1.762 |  |  |  | 4.405
Shawfair Bellway Plots E2 & F1 - MMR - Phase 1: P44577 | B | Medium | X - 331600 Y - 669798 |  | PFP |  | 16 |  |  |  |  | 16 |  |  | 16 | 16 | 16 |  |  | 16 | Y | 2026/27 | 16 |  |  |  |  | 16 |  |  | 16 |  |  | 16 | 1.037 | 0.691 |  |  |  | 1.728
Shawfair Bellway Plot F2 - SR - Phase 2: P44576 | B | Medium | X - 331784 Y - 669962 |  | PFP | 26 | [5 empty] | 26 |  |  | 26 | 26 | 26 |  |  | 26 | Y | 2027/28 |  | 26 |  |  |  | 26 |  |  |  | 26 |  | 26 |  | 1.322 | 3.083 |  |  | 4.405
Shawfair Bellway Plot F2 - MMR - Phase 2: P44578 | B | Medium | X - 331784 Y - 669962 |  | PFP |  | 16 |  |  |  |  | 16 |  |  | 16 | 16 | 16 |  |  | 16 | Y | 2027/28 |  | 16 |  |  |  | 16 |  |  |  | 16 |  | 16 |  | 0.518 | 1.21 |  |  | 1.728
Old Craighall Road, Millerhill - Barratt - SR: P43839 | B | Medium | X - 332522 Y - 669598 |  | PFP | 21 | [5 empty] | 21 |  |  | 21 | 21 | 21 |  |  | 21 |  | 2027/28 |  | 21 |  |  |  | 21 |  |  | 21 |  |  | 21 |  | 2.039 | 0.51 |  |  | 2.549
Old Craighall Road, Millerhill - Barratt - MMR: P41773 | B | Medium | X - 332522 Y - 669598 |  | PFP |  | 9 |  |  |  |  | 9 |  |  | 9 | 9 | 9 |  |  | 9 |  | 2027/28 |  | 9 |  |  |  | 9 |  |  | 9 |  |  | 9 |  | 0.638 | 0.159 |  |  | 0.797
Dalhousie South Ph1: P43743 | B | Medium | 55.870857, -3.084838 | 3 | WHE | 30 | [5 empty] | 30 |  |  | 30 | 30 | 30 | 0 |  | 30 | Y | 2025/26 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0
Dalhousie South Ph2a: P47189 | B | High | 55.870857, -3.084838 | 3 | WHE | 26 | [5 empty] | 26 |  |  | 26 | 26 | 18 | 8 | wheelchair/amenity | 26 | Y | 2025/26 | [5 empty] | 0 | 26 |  |  |  |  | 26 | 2.275 |  |  |  |  | 2.275
Dalhousie South Ph2b: P47190 | B | high | 55.870857, -3.084839 | 3 | WHE | 24 | [5 empty] | 24 |  |  | 24 | 24 | 24 |  |  | 24 | y | 2026/27 | 24 |  |  |  |  | 24 |  | 24 |  |  |  | 24 |  | 3 |  |  |  | 3
Auchendinny Phase 2 | Auchendinny | High | 55.848423, -3.186239 | 3 | WHE | 20 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 20 | 0 | 14 | 6 | amenity | 20 | Y | 2026/27 | 0 | 0 | 20 | 0 | 0 | 20 | 0 | 0 | 0 | 20 | 0 | 20 |  |  | 1.5 | 0.68 |  | 2.18
Auchendinny Phase 1: P41924 | A | High | 55.848423, -3.186240 | 3 | WHE |  | 24 |  |  |  |  | 24 |  |  | 24 | 24 | 24 |  |  | 24 | Y | 2025/26 | 24 |  |  |  |  | 24 | 24 |  |  |  |  | 24 | 1.777 |  |  |  |  | 1.777
Shawfair Town Centre: P41782 P44798 | B | Medium | 55.916239, -3.093542 | 3 | WHE | 70 | 30 |  |  |  |  | 100 |  |  | 100 | 100 | 80 | 20 | amenity | 100 | Y | 2027/28 |  |  |  | 100 |  | 100 |  |  |  |  | 25 | 25 |  |  |  | 3 | 3 | 6
Wellington School, Penicuik: P47215 | A | low | 55.797796, -3.216936 | 3 | WHE | 12 | [5 empty] | 12 |  |  | 12 | 12 | 11 | 1 | Wheelchair | 12 | Y | 2027/28 |  | 12 |  |  |  | 12 |  |  | 12 |  |  | 12 |  | 1.392 |  |  |  | 1.392
Old Craighall Road, Shawfair (Mactaggart and Mickel). P41836 | B | Low | 55.913119, -3.086424 | 3 | WHE | 48 | [5 empty] | 48 |  |  | 48 | 48 | 46 | 2 | WFS | 48 | Y | 2029/30 |  |  |  | 48 |  | 48 |  |  |  |  | 20 | 20 |  |  |  | 2.0544 | 3.0816 | 5.136
Thornybank: P47836 | B | Medium | X 334706 Y 667649 | 2 | Link | 33 | [5 empty] | 33 |  |  | 33 | 33 | 30 | 3 | wheelchair | 33 | Y | 2025/26 | 33 |  |  |  |  | 33 |  | 33 |  |  |  | 33 | 2 | 2.479 |  |  |  | 4.479
Pods C and B2, Craighall Village, Millerhill (Cala): P43726 | B | High | X: 333025 Y: 669998 | 5 | TBC | 46 | [5 empty] | 46 |  |  | 46 | 46 | 46 |  |  | 46 | Y | 2026/27 | 46 |  |  |  |  | 46 |  | 46 |  |  |  | 46 | 2.343 | 2.343 |  |  |  | 4.686 | UPDATED AS PER EMAILS. REMOVED WHE & PFP PROJECTS and deleted future AH units as not in RSL returns
Total | [5 empty] | 1322 | 261 | 0 | 0 | 0 | 0 | 1583 | 0 | 30 | 1553 | 1583 | 1430 | 153 | 0 | 1583 |  |  | 503 | 287 | 81 | 227 | 68 | 1166 | 205 | 420 | 304 | 118 | 135 | 1182 | 36.1815 | 42.7608 | 21.061 | 17.13 | 10.0436 | 127.178
Drop Down Table Values
Numerical Value | Geographic Code
1 | Large urban area
2 | Other urban area
3 | Accessible small town
4 | Remote small town
5 | Accessible rural area
6 | Remote rural area
Note on AN32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Estimating 6 SG funded OMPs per year

## TABLE 2 - HIF PROJECTS
MORE HOMES DIVISION
Table 2 - HOUSING INFRASTRUCTURE FUND (HIF) PROJECTS
Note: Projects should be entered as either Grant or Loan - Any which state a mixed category e.g. Grant/Loan or Grant or Loan will not be considered
TABLE 2.1 - GRANT PROJECTS
[9 empty] | AFFORDABLE HOUSING UNITS DIRECTLY PROVIDED BY INFRASTRUCTURE FUNDING - BY ESTIMATED COMPLETION DATE | [14 empty] | HIF GRANT FUNDING REQUIRED |  |  |  |  | POTENTIAL ADDITIONAL CAPACITY - UNITS NOT DIRECTLY FUNDED BUT UNLOCKED BY INFRASTRUCTURE FUNDING
PROJECT | PRIORITY | GEOGRAPHIC COORDINATES (X:EASTING Y:NORTHING) | APPLICANT | PLANNING STATUS (OUTLINE/ MASTERPLAN/ FULL CONSENT IN PLACE) (Y/N) | DOES APPLICANT OWN OR HAVE POTENTIAL TO OWN THE SITE? (Y/N) | CURRENT SITE OWNER | BRIEF DESCRIPTION OF WORKS FOR WHICH INFRASTRUCTURE FUNDING IS SOUGHT (PROVIDE WORK HEADINGS - DO NOT INSERT "INFRASTRUCTURE WORKS") | IS PROJECT LINKED TO DIRECT PROVISION OF AFFORDABLE HOUSING? (Y/N) | AFFORDABLE |  |  |  |  | MARKET |  |  |  |  | PRIVATE RENT
| Low / Medium / High | [7 empty] | 2026/27 | 2027/28 | 2028/29 | POST 2029/30 | AFFORDABLE TOTAL OVER PLAN OVER SHIP PERIOD | 2026/27 | 2027/28 | 2028/29 | POST 2029/30 | MARKET TOTAL OVER PLAN OVER SHIP PERIOD | 2026/27 | 2027/28 | 2028/29 | POST 2029/30 | PRIVATE RENT TOTAL OVER PLAN OVER SHIP PERIOD | 2026/27 | 2027/28 | 2028/29 | POST 2029/30 | TOTAL HIF GRANT FUNDING REQUIRED | UNITS - POTENTIAL ADDITIONAL CAPACITY IN EITHER LATER PHASES OR OTHER SITES | TENURE - AFFORDABLE / MARKET /PRIVATE RENTED
[13 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
Total | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TABLE 2.2 - LOAN PROJECTS
[9 empty] | AFFORDABLE HOUSING UNITS DIRECTLY PROVIDED BY INFRASTRUCTURE FUNDING - BY ESTIMATED COMPLETION DATE | [14 empty] | HIF LOAN FUNDING REQUIRED |  |  |  |  | POTENTIAL ADDITIONAL CAPACITY - UNITS NOT DIRECTLY FUNDED BUT UNLOCKED BY INFRASTRUCTURE FUNDING
PROJECT | PRIORITY | GEOGRAPHIC COORDINATES (X:EASTING Y:NORTHING) | APPLICANT | PLANNING STATUS (OUTLINE/ MASTERPLAN/ FULL CONSENT IN PLACE) (Y/N) | DOES APPLICANT OWN OR HAVE POTENTIAL TO OWN THE SITE? (Y/N) | CURRENT SITE OWNER | BRIEF DESCRIPTION OF WORKS FOR WHICH INFRASTRUCTURE FUNDING IS SOUGHT (PROVIDE WORK HEADINGS - PLEASE "INFRASTRUCTURE WORKS") | IS PROJECT LINKED TO DIRECT PROVISION OF AFFORDABLE HOUSING? (Y/N) | AFFORDABLE |  |  |  |  | MARKET |  |  |  |  | PRIVATE RENT
| Low / Medium / High | [7 empty] | 2025/26 | 2026/27 | 2027/28 | POST 2028/29 | AFFORDABLE TOTAL OVER PLAN OVER SHIP PERIOD | 2025/26 | 2026/27 | 2027/28 | POST 2028/29 | MARKET TOTAL OVER PLAN OVER SHIP PERIOD | 2025/26 | 2026/27 | 2027/28 | POST 2028/29 | PRIVATE RENT TOTAL OVER PLAN OVER SHIP PERIOD | 2025/26 | 2026/27 | 2027/28 | POST 2028/29 | TOTAL HIF LOAN FUNDING REQUIRED | UNITS - POTENTIAL ADDITIONAL CAPACITY IN EITHER LATER PHASES OR OTHER SITES | TENURE - AFFORDABLE / MARKET /PRIVATE RENTED
[13 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
[13 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
Total | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## TABLE 3 - HIF AFFORDABLE HSG
MORE HOMES DIVISION
STRATEGIC HOUSING INVESTMENT PLAN 2026/27- 2030/31
Table 3 - POTENTIAL HIF AFFORDABLE HOUSING PROJECTS WHICH MAY BE DEVELOPED FOLLOWING HIF INVESTMENT
LOCAL AUTHORITY: Midlothian
PROJECT | SUB-AREA | PRIORITY | GEOGRAPHIC COORDINATES (X:EASTING Y:NORTHING) | GEOGRAPHIC CODE (Numeric Value - from Drop Down Table Below) | DEVELOPER | UNITS - TENURE | [6 empty] | UNITS - BUILT FORM |  |  |  | UNITS - TYPE |  |  |  | GREENER STANDARDS | APPROVAL DATE | UNIT SITE STARTS |  |  |  |  | UNITS - COMPLETIONS |  |  |  |  | SG AHSP FUNDING REQUIREMENT (£0.000M)
|  | Low / Medium / High |  |  |  | Social Rent | Mid Market Rent | LCHO - Shared Equity | LCHO - Shared Ownership | LCHO - Improvement for Sale | PSR | Total Units | Rehab | Off the Shelf | NB | Total Units | GN | Specialist Provision | Type of Specialist Particular Need (If Known) | Total Units by Type | Enter Y or N | Financial Year (Estimated or Actual) | 2026/27 | 2027/28 | 2028/29 | POST 2029/30 | TOTAL SITE STARTS OVER PERIOD OF SHIP | 2026/27 | 2027/28 | 2028/29 | POST 2029/30 | TOTAL COMPLETIONS OVER PERIOD OF SHIP | 2026/27 | 2027/28 | 2028/29 | POST 2029/30 | TOTAL AHSP FUNDING REQUIRED OVER SHIP PERIOD
Total | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drop Down Table Values
[21 empty] | Numerical Value | Geographic Code
[21 empty] | 1 | West Highland/Island Authorities/Remote/Rural Argyll -RSL - SR - Greener |  |  |  | RSL - SR - Greener
[21 empty] | 2 | West Highland/Island Authorities/Remote/Rural Argyll |  |  |  | RSL - SR - Other
[21 empty] | 3 | Other Rural |  |  |  | RSL - SR - Greener
[21 empty] | 4 | Other Rural |  |  |  | RSL - SR - Other
[21 empty] | 5 | City and Urban |  |  |  | RSL - SR - Greener
[21 empty] | 6 | City and Urban |  |  |  | RSL - SR - Other
[21 empty] | 7 | All |  |  |  | RSL - Mid-Market Rent - Greener
[21 empty] | 8 | All |  |  |  | RSL - Mid-Market Rent - Other
[21 empty] | 9 | All |  |  |  | Council - SR - Greener
[21 empty] | 10 | All |  |  |  | Council -SR - Other

## TABLE 4 - NON-AHSP PROJECTS
MORE HOMES DIVISION
STRATEGIC HOUSING INVESTMENT PLAN 2026/27 - 2030/31
LOCAL AUTHORITY: Midlothian
TABLE 4 - AFFORDABLE HOUSING PROJECTS FUNDED OR SUPPORTED BY SOURCES OTHER THAN THE RPA/TMDF BUDGET
PROJECT ADDRESS | SUB-AREA | PRIORITY | GEOGRAPHIC COORDINATES (X:EASTING Y:NORTHING) | DEVELOPER | FUNDING SUPPORT SOURCE | APPROVAL DATE | [5 empty] | TOTAL | UNIT COMPLETIONS |  |  |  |  | TOTAL UNIT COMPLETIONS | NON SG FUNDING TOTAL £0.000M | OTHER NON-AHSP SG FUNDING (IF APPLICABLE) £0.000M | TOTAL FUNDING £0.000M
|  | Low / Medium / High |  |  |  | Financial Year (Actual or Estimated) | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31 | TOTAL SITE STARTS | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31
Wester Cowden |  |  | 335139: 667131 | Lar | TBC/PF |  | 15 |  |  |  |  | 15 |  |  | 15 |  |  | 15 |  | TBC | 1.44
Fordel |  |  | 336078: 666742 | Lar | TBC/PF |  | 24 |  |  |  |  | 24 |  |  | 24 |  |  | 24 |  | TBC | 2.16
[12 empty] | 0 | [5 empty] | 0 |  |  | 0
[12 empty] | 0 | [5 empty] | 0 |  |  | 0
[12 empty] | 0 | [5 empty] | 0 |  |  | 0
[12 empty] | 0 | [5 empty] | 0 |  |  | 0
[12 empty] | 0 | [5 empty] | 0 |  |  | 0
[12 empty] | 0 | [5 empty] | 0 |  |  | 0
[12 empty] | 0 | [5 empty] | 0 |  |  | 0
[12 empty] | 0 | [5 empty] | 0 |  |  | 0
Total | [6 empty] | 39 | 0 | 0 | 0 | 0 | 39 | 0 | 0 | 39 | 0 | 0 | 39 | 0 | 0 | 3.6